## Sheet1
Video detailing this method: | Time of Completion = 206 Days | Critical Path Method
https://www.youtube.com/watch?v=Nso8yZOlnjg | 20/11/2023 - 13/6/2024 | Activity | Decide parameters and gather equations | Familiarise with FIJI | Data storage method | Literature reviews | Gather data | Calculate parameters | MATLAB analysis | Progress report | Write report | Make presentation slides
| Project plan due date - Presentation due date | Activity No. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
|  | Predecessor Activity (PA) | --- | --- | --- | 1,2 | 3,4 | 5 | 6 | 5 | 3,6 | 9
| Time to first deadline = 122 Days (Progress report) | Duration (Time in days) | 14 | 14 | 21 | 14 | 14 | 7 | 28 | 14 | 21 | 14
|  | Early Start (ES) | 0 | 0 | 0 | 14 | 28 | 42 | 49 | 42 | 77 | 98
|  | Early Finish (EF) | 14 | 14 | 21 | 28 | 42 | 49 | 77 | 56 | 98 | 112
|  | Successor Activity (SA) | 4 | 4 | 5,9 | 5 | 6 | 7 | 8 | 9 | 10 | ---
|  | Late Start (LS) | 17 | 31 | 38 | 45 | 59 | 73 | 80 | 108 | 171 | 192
|  | Late Finish (LF) | 31 | 45 | 59 | 59 | 73 | 80 | 108 | 122 | 192 | 206
|  | Slack | 17 | 31 | 38 | 31 | 31 | 31 | 31 | 66 | 94 | 94